## MeetingTracker
Group Number: 3 |  | Project Name: Beat Box
Project Manager (s): Micheal Kempner
Meeting Date | Attendees | Absent | Topic Discussed | Additional Notes
2023-01-23 | Ashlee K. Micheal K. Michael U. | Rayan B. | Project idea and direction. Division of labor for first assignment
2023-01-30 | Rayan B. Ashlee K. Micheal K. Michael U. | None | Deliverables for assignment 1 discussed. Assignment 2 instructions were reviewed. Each member will independently brainstorm as many business events, business use cases, and initial features as they could and bring them to the next meeting | The following deliverables were not at delivered at the meeting. They must be delivered to PM by 5:00 pm today January 30th, 2023. Any deliverables received after that time will not be included in the assignment submission. This is to give the PM time to review and assemble the deliverables for submission to Dr. Smith at 9:00am on January 31st, 2023. | Bio information and photo - Rayan B, Ashlee K Presentation slides - Rayan B, Ashlee K, Michael U Introduction video - Rayan B, Ashlee K, Michael U Presentation video - Rayan B, Ashlee K, Michael U Work context diagram - Rayan B Stakeholder mapping - Ashlee K Team Bio - Michael U (Blocker: Need info and photos from Rayan B and Ashlee K)

## AssignmentTracker
Group Number: 3 |  |  |  |  | Project Name: Beat Box
Project Manager (s): Annie R.
Assignment # | Assignments Deliverables | Owner | Assigned Date | Due Date | Delivered? | Comments
1 | SOW | Micheal K | Jan 23rd | Jan 30th | Yes | Will post draft by Jan 25th
1 | Work Context Diagram | Rayan B | Jan 23rd | Jan 30th | Pending
1 | Stakeholder Mapping | Ashlee K | Jan 23rd | Jan 30th | Pending
1 | Team Profile Page | Michael U | Jan 23rd | Jan 30th | Pending | Please send picture, hometown, Primary focus, internship position (if applicable), fun fact ASAP
1 | Video Introduction | All | Jan 23rd | Jan 30th | Pending | Record brief video in .mp4 for profile
1 | Presentation Video | All | Jan 23rd | Jan 30th | Pending | Record yourself presenting your slides
1 | Presentation Slides | All | Jan 23rd | Jan 30th | Pending | Complete your slides for your portion of the presentation
2 | Business Events\Use Cases | All | Jan 30th | Feb 6th | Pending | Independently brainstorm as many events and use cases as you can. Document them all somehow (pdf, docx, etc).
2 | Initial Feature Set | All | Jan 30th | Feb 6th | Pending | Independently brainstorm as many features as you can. Document them all somehow (pdf, docx, etc).